## Sheet1
Sprint 2 - 14 Days
Dublin Bikes Features & Functions | Work Hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
Create a Google Maps API All | 20 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2
a) All members create Maps API
b) Set up an API key, test on app.py
c) Save API key offline (local machine)
Weather API - GUO | 20 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 1 | 1 | 3 | 1 | 1 | 1
a) All members create OpenWeather API
b) Rhys create OpenWeather function
c) Test API key on OpenWeather and verify
HTML/CSS JIN | 20 | 2 |  | 3 |  |  | 1 | 1 | 1 | 5 | 5 |  |  | 1 | 1
a) Edit html file to include JS script
Migrate EC2 to new EC2 - JIN/GUO | 20 | 2 | 2 | 1 | 2 | 2 | 2 | 1 | 1 |  | 1 | 2 | 1 | 2 | 1
a) Connect
b) SSH into EC2
FLASK ALL | 40 | 1 | 1 |  | 1 | 1 |  | 1 | 1 | 1 | 1 |  | 4 | 4 | 4
a) Rhys create flask app.py
b) Everyone contribute to adding functions and decorators
c) Guo connect new EC2 to flask
d) Test flask app on EC2 to verify web server
b) Keep branches up to date
Project Management - JIANG | 20 | 1 | 1 | 1 |  | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3
a) 5 x meetings per week (30 mins)
b) Start an SRS
c) Start a Dbikes report journal
Make burndown charts
Time Taken | 120 | 8 | 6 | 7 | 5 | 8 | 8 | 7 | 7 | 10 | 11 | 8 | 10 | 13 | 12
120
[13 empty] | GUO | JIN | JIANG
[13 empty] | 45 | 41 | 34

## Sheet2
Feature_Sprint 2 | Importance | Comment
Create a Google Maps API All
a) All members create Maps API | 8 | Guo and Jin have payment errors on that.
b) Set up an API key, test on app.py | 7 | On hold
c) Save API key offline (local machine) | 7 | On hold
Weather API - GUO
a) All members create OpenWeather API | 9
b) Rhys create OpenWeather function | 7
c) Test API key on OpenWeather and verify | 6
HTML/CSS JIN
a) Edit html file to include JS script | 6 | Just do the framework this print
Migrate EC2 to new EC2 - JIN/GUO
a) Connect | 9
b) SSH into EC2 | 7
FLASK ALL
a) Rhys create flask app.py | 10
b) Everyone contribute to adding functions and decorators | 7
c) Jin connect new EC2 to flask | 7
d) Test flask app on EC2 to verify web server | 7
b) Keep branches up to date | 7
Project Management - JIANG
a) 5 x meetings per week | 5
b) Start an SRS | 7
c) Start a Dbikes report journal | 7
Make burndown charts | 7