## Sheet1
Sprint 1 - 14 Days
Dublin Bikes Features & Functions | Work Hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
Dublin Bikes API Jiang | 25 | bar: Day 1 to Sprint 1 - 14 Days Day 14
a) Create a scraper
b) Upload scraper to GitHub
c) Test the scraper on EC2
Weather API GUO | 25 | bar: Day 1 to Sprint 1 - 14 Days Day 14
a) Create a scraper
b) Upload scraper to GitHub
c) Test the scraper on EC2
HTML/CSS JIN | 5 | bar: Day 1 to Sprint 1 - 14 Days Day 14
a) Send a skeleton to GitHub
EC2 Jin/Guo | 15 | bar: Day 1 to Sprint 1 - 14 Days Day 14
a) Set up an EC2 Instance
b) SSH into EC2
RDS Jiang/Guo | 15 | bar: Day 1 to Sprint 1 - 14 Days Day 14
a) Create an RDS database
b) Connect to mySQL
GitHub Jin/JIANG | 10 | bar: Day 1 to Sprint 1 - 14 Days Day 14
a) Set it up
b) Create branches
Requirements All | 40 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 3 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 3
a) 5 x meetings per week (30 mins)
b) Start an SRS
c) Create an SRS
d) Create user stories
Time Taken | 130 | 8.5 | 8.5 | 8.5 | 8.5 | 8.5 | 8.5 | 9 | 8.5 | 8.5 | 8.5 | 8.5 | 8.5 | 8.5 | 9
120
[13 empty] | Jin | Guo | JIANG
[13 empty] | 40 | 40 | 40