## Sprint4
Sprint 2 - 14 Days
Dublin Bikes Features & Functions | Work Hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
Confirm the prediction works well GUO | 30 | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | 5 | 5
HTML/CSS JIN | 20 | Day 1: 2; Sprint 2 - 14 Days Day 2: 2; Sprint 2 - 14 Days Day 3: 3; Sprint 2 - 14 Days Day 4: 3; Sprint 2 - 14 Days Day 6: 2; Sprint 2 - 14 Days Day 7: 2; Sprint 2 - 14 Days Day 8: 3; Sprint 2 - 14 Days Day 9: 3
a) Make the final version of the Homepage
Web Application ALL | 40 | Sprint 2 - 14 Days Day 3: 5; Sprint 2 - 14 Days Day 4: 5; Sprint 2 - 14 Days Day 5: 5; Sprint 2 - 14 Days Day 6: 5; Sprint 2 - 14 Days Day 7: 5; Sprint 2 - 14 Days Day 8: 5; Sprint 2 - 14 Days Day 9: 5; Sprint 2 - 14 Days Day 10: 5
a) Find cloesst bike
b) Charts clean up
c) issue with the bugs from the map
d) Test flask app on EC2 to verify web server
b) Keep branches up to date
Project Management - JIANG | 30 | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  |  |  | 3 | 3 | 3
b) Finish a SRS
c) Finish the Report
Make burndown charts
Time Taken | 120 | 7 | 7 | 13 | 13 | 10 | 10 | 10 | 10 | 10 | 7 | 5 | 5 | 8 | 5
120
[13 empty] | GUO | JIN | JIANG
[13 empty] | 40 | 40 | 40

## Sprint3
Sprint 3 - 14 Days
Dublin Bikes Features & Functions | Work Hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
Organizing and archiving data - GUO | 20 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
a) Debugging and refining local databases
b) Monitoring whether new data can be stored properly
c) Optimizing the update frequency of data
Machine Learning - GUO | 20 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 2 | 1 | 1 | 1
a) Selecting data attributes that are effective
b) Utilizing random forests for machine learning
c) Observing the results of the initial
HTML/CSS JIN | 20 | Day 1: 3; Sprint 3 - 14 Days Day 3: 3; Sprint 3 - 14 Days Day 6: 1; Sprint 3 - 14 Days Day 7: 3; Sprint 3 - 14 Days Day 8: 3; Sprint 3 - 14 Days Day 9: 3; Sprint 3 - 14 Days Day 10: 3; Sprint 3 - 14 Days Day 14: 1
a)show the occupancy of individual station marker
b)show the selection of specific station on the map
Visuailising data with dynamic chars - JIN/JIANG | 20 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 2 | 1 | 2 | 1
a) Constructing a line graph distributed by hour.
b) Constructing a bar graph distributed by date.
Methods on the web page - All | 20 | 1 | 1 |  | 1 | 1 | 3 | 3 | 3 | 1 | 1 |  | 2 | 2 | 1
a) distance measurement between users and stations
b) Integrate bikes and weather data
c) design for the background and color of page
d) Test all the buttoms on the page
b) Keep branches up to date
Project Management - JIANG | 20 | 1 |  | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 2 | 2 | 2 | 2 | 2
a) meetings per week (60 mins)
b) Start the report
c) update the SRS document
Make burndown charts
Time Taken | 120 | 9 | 5 | 8 | 8 | 8 | 12 | 14 | 12 | 9 | 10 | 6 | 6 | 7 | 6
120
[13 empty] | GUO | JIN | JIANG
[13 empty] | 42 | 41 | 37

## Sprint2
Sprint 2 - 14 Days
Dublin Bikes Features & Functions | Work Hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
Create a Google Maps API All | 20 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2
a) All members create Maps API
b) Set up an API key, test on app.py
c) Save API key offline (local machine)
Weather API - GUO | 20 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 1 | 1 | 3 | 1 | 1 | 1
a) All members create OpenWeather API
b) Guo create OpenWeather function
c) Test API key on OpenWeather and verify
HTML/CSS JIN | 20 | 2 |  | 3 |  |  | 1 | 1 | 1 | 5 | 5 |  |  | 1 | 1
a) show the occupancy of individual station marker
Migrate EC2 to new EC2 - JIN/GUO | 20 | 2 | 2 | 1 | 2 | 2 | 2 | 1 | 1 |  | 1 | 2 | 1 | 2 | 1
a) Connect
b) SSH into EC2
FLASK ALL | 40 | 1 | 1 |  | 1 | 1 |  | 1 | 1 | 1 | 1 |  | 4 | 4 | 4
a) Jin create flask app.py
b) Everyone contribute to adding functions and decorators
c) Guo connect new EC2 to flask
d) Test flask app on EC2 to verify web server
b) Keep branches up to date
Project Management - JIANG | 20 | 1 | 1 | 1 |  | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 3
a) 5 x meetings per week (30 mins)
b) Start an SRS
c) Start a Dbikes report journal
Make burndown charts
Time Taken | 120 | 8 | 6 | 7 | 5 | 8 | 8 | 7 | 7 | 10 | 11 | 8 | 10 | 13 | 12
120
[13 empty] | GUO | JIN | JIANG
[13 empty] | 45 | 41 | 34

## Sheet2
Feature_Sprint 2 | Importance | Comment
Create a Google Maps API All
a) All members create Maps API | 8 | Guo and Jin have payment errors on that.
b) Set up an API key, test on app.py | 7 | On hold
c) Save API key offline (local machine) | 7 | On hold
Weather API - GUO
a) All members create OpenWeather API | 9
b) Rhys create OpenWeather function | 7
c) Test API key on OpenWeather and verify | 6
HTML/CSS JIN
a) Edit html file to include JS script | 6 | Just do the framework this print
Migrate EC2 to new EC2 - JIN/GUO
a) Connect | 9
b) SSH into EC2 | 7
FLASK ALL
a) Rhys create flask app.py | 10
b) Everyone contribute to adding functions and decorators | 7
c) Jin connect new EC2 to flask | 7
d) Test flask app on EC2 to verify web server | 7
b) Keep branches up to date | 7
Project Management - JIANG
a) 5 x meetings per week | 5
b) Start an SRS | 7
c) Start a Dbikes report journal | 7
Make burndown charts | 7